## Sheet1
RESULTS-BASED ACTION PLAN
For FY 2026
A. BASIC INFORMATION
ITEM |  | DETAILS
Campus |  | University-wide
Office/Unit |  | Information Technology and Communication Unit
Program/Project/Activity/KRA |  | General Administration and Support
Strategic Alignment/Planning Document |  | CHMSU Strategic Plan 2025-2029/Information System Strategic Plan
Breakthrough Goals |  | Digital and Technology Transformation
Strategic Objectives |  | To integrate smart, safe, and sustainable technologies in the university’s operations, systems, land use, and campus infrastructure developments.
Planning Year |  | 2026
Date Prepared |  | 2026-01-26
B. RESULTS-BASED ACTION PLAN MATRIX
Result Level | Target Result (SMART) | Key Actions/Activities | Key Risk | Mitigation/Control Measures | Key Performance Output/Outcome Indicators | Target | Responsible Office/Person | Timeline | Fund Source | Budget Requirements | Budget Allocation | Budget Deficit | Means of Verification (MOV)
Outcome A | Enhanced ICT infrastructure that supports efficient service and quality teaching-learning activities | Implement ICT infrastructure projects aligned to ISSP. | Limited budget to allocate for procuring ICT infrastructure projects | Seek external funding from other government agencies | Number of ICT infrastructure projects implemented | 10 ICT infrastructure projects | ICT-ITS, ICT-MIS | 4th qtr 2026 | GAA/Income | 4266000 | 971200 | 3294800 | Purchase Request/ Purchase Order/ Completion Report and Certificate
Output A.1 | Innovative ICT infrastructure projects | Conduct market research on prospective suppliers; Request for site survey; | No local suppliers may provide the purchase request | Request for local authorized dealer/reseller for suppliers outside Negros Island | Number of ICT infrastructure projects implemented based on the approved ISSP | six (6) implemented ICT infra projects from ISSP | ICT-ITS | 4th qtr 2026 | GAA/Income | 7170000 | 6370000 | 800000 | Purchase Request/ Purchase Order/ Completion Report and Certificate
Output A.2 | Improved computer laboratory and facilities | Conduct market research on prospective suppliers; Request for site survey; | Delays in delivery and setup of computers in the laboratory | Close coordination with the supplier to monitor progress and observance of project timeline | Number of upgraded and enhanced computer laboratory and facilities | four (4) upgraded/ enhanced computer labs | ICT-ITS | 4th qtr 2026 | GAA/Income | 6820000 | 6355000 | 465000 | Purchase Request/ Purchase Order/ Completion Report and Certificate
Outcome B | Established operational secured, centralized, energy-efficient ICT infrastructure | Create a cybersecurity plan that secures the centralized network; Proper use of energy-savings facilities | Security breaches; hardware failures and deteriorations | Regular monitoring of system security; hardware maintenance | Number of network, cybersecurity, and energy-efficient ICT projects | three (3) network-related and cost-effective ICT projects | ICT-ITS, ICT-MIS | 3rd qtr 2026 | GAA/Income | 0 | 0 | 0 | Completion Report and Certificate/ Cybersecurity Plan
Output B.1 | Efficient and secure system-wide centralized network | Design and setup the centralized network infrastructure; Implement cybersecurity measures | System vulnerabilities | Regular seminar/ training on cybersecurity; Updated cybersecurity tools | Number of installed infrastructures to support the system-wide centralization of network and enhanced cybersecurity | two (2) network- and cybersecurity-related projects | ICT-ITS, ICT-MIS | 2nd qtr 2026 | GAA/Income | 15000000 | 15000000 | 0 | Purchase Order/ Completion Report and Certificate/ Cybersecurity Plan
Output B.2 | Cost-effective and energy-saving ICT installed equipment | Install equipment; Generate report on energy cost savings | Hardware failures and deteriorations | Regular hardware maintenance | Number of ICT facilities utilizing cost saving and renewable power source | one (1) ICT cost-saving or renewable energy projects | ICT-ITS | 3rd qtr 2026 | GAA/Income | 500000 | 500000 | 0 | Completion Report and Certificate
Outcome C | digitalized and accessible online university services | Deploy information systems in local or cloud server; document the system | System vulnerabilities; Issue on software and hardware compatibilities | Updated security tools; Upgrade system for software and hardware compatibility | Number of information systems implemented in cloud and local hosting | eight (8) information systems to be deployed locally and on cloud | ICT-MIS | 4th qtr 2026 | GAA/Income | 0 | 0 | 0 | Certificate of Deployment/ User Manual
Output C.1 | Streamlined transactions via information systems | Enhance the code and build the information system of the university | Limited skills and manpower | Training and upskilling of developers | Number of upgraded, developed and deployed information systems and digitalized process/procedures. | five (5) deployed information systems | ICT-MIS | 4th qtr 2026 | GAA/Income | 3000000 | 3000000 | 0 | Certificate of Deployment/ User Manual
Output C.2 | Accessible and available of university services and resources | Deploy the university services on cloud server | Slow system performance | Upgrade software and hardware components | Number of university services deployed via cloud computing | three (3) university online services | ICT-MIS | 4th qtr 2026 | GAA/Income | 0 | 0 | 0 | Certificate of Deployment/ User Manual
Outcome D | Digitized, secure, and continuously available university services supporting instruction, research, and administration through licensed productivity, collaboration, research, AI, and cybersecurity subscriptions | Procure, renew, configure, deploy, and manage institutional subscription licenses; integrate platforms into university ICT infrastructure; enforce usage and security policies | Underutilization of subscriptions | Centralized ICT governance; regular security updates; user orientation and access controls; vendor support and SLAs | Number of licenses purchase | 500 licenses purchased | ICT-MIS | 4th qtr 2026 | GAA/Income | 0 | 0 | 0 | Purchase Request/ Purchase Order/
Output D.1 | Streamlined academic, research, and administrative processes enabled by licensed digital platforms | Implement and maintain Zoom, Google Workspace, Microsoft 365, Research Archiving System, AI tools | Unhandled subscription credentials and undercapacity of subscription | Managed and monitored list of credentials utilized or installed | Number of licenses installed | 500 licenses installed | ICT-MIS | 4th 2026 | GAA/Income | 1140000 | 290000 | 850000 | Accoun Credntials Inventory
Output D.2 | Strengthened cybersecurity posture of university systems and networks | Conduct regular vulnerability assessments; monitor endpoints and network traffic; enforce security controls; firewall, endpoint security, and VAPT software | Data breach; malware infection; system compromise | Endpoint monitoring; firewall rule management; vulnerability remediation | Number of cybersecurity attack attempts scanned | 350 attack attempts scanned | ICT-MIS | 1st qtr 2026 | GAA/Income | 2323600 | 50000 | 2273600 | Vulnerability Scanning Report
C. MONITORING
ITEM |  | DETAILS
Monitoring Frequency |  | Quarterly
Reporting Office |  | Information and Communication Technology Unit Information Technology Services Unit Management Information System Unit
| Prepared by: |  |  | Reviewed by: |  |  |  | Approved by:
| ARIANE M. TORRES, MIT | [6 empty] | NORBERTO P. MANGULABNAN, PhD
| Division/Unit Head/Dean |  |  | Vice President |  |  |  | SUC III President