## Sheet1
RESULTS-BASED ACTION PLAN
For FY 2026
A. BASIC INFORMATION
ITEM |  | DETAILS
Campus |  | University-wide
Office/Unit |  | Project Management Unit
Program/Project/Activity/KRA |  | Construction and Enhancement/Rehabilitation Program
Strategic Alignment/Planning Document |  | CHMSU Strategic Plan 2025-2029
Breakthrough Goals |  | Good Governance
Strategic Objectives |  | To integrate smart, safe, and sustainable technologies in the university’s operations, systems, land use, and campus infrastructure development.
Planning Year |  | 2026
Date Prepared |  | January 13, 2026
B. RESULTS-BASED ACTION PLAN MATRIX
Result Level | Target Result (SMART) | Key Actions/Activities | Key Risk | Mitigation/Control Measures | Key Performance Output/Outcome Indicators | Target | Responsible Office/Person | Timeline | Fund Source | Budget Requirements | Budget Allocation | Budget Deficit | Means of Verification (MOV)
Outcome: Strengthened planning, compliance, and delivery of new infrastructure and enhancement/rehabilitation programs
Output 1 | To establish a plan to making sure that land resources are efficiently utilized for any kind of land use activity. | Timely procurement of CO infrastructure projects | Procurement delays and failed biddings | Prepare a detailed procurement timetable aligned with the CO implementation schedule and closely monitor milestones. | Percentage of CO projects procured on schedule | 100% on time procurement | PMU, BAC | 1st -3rd Quarter | GAA STF
|  | Implement 2026 Infrastructure Project Construction of Academic Building (Business Complex Phase 1 – Fortune Towne Campus) | Slippage in construction schedules and scope variations | Regular site inspections and contractor monitoring | Percentage of accomplishment on Capital Outlay (CO) infrastructure projects at the end of the Fiscal Year | 60% December 2026 | PPDM | 4th quarter | GAA | 70M | 54.803M | 15.2M
Output 2 | Establish a functional facility to accommodate the needs of the academic community | Assess existing facilities and identify repair and maintenance requirements | Incomplete or inaccurate assessment | Use standard facility assessment checklist; coordination with end-users | Number of existing facilities / infrastructure enhanced or improved. | *Alijis: 9 *Fortune Towne: 7 *Binalbagan: 9 *Talisay: 11 Total: 36 | PPDM | 1st-4th qrter | GAA | •Alijis:3.4M •Fortune Towne: 3.30M •Binalbagan: 3.47M •Talisay: 6.19M Total: 16.36M
Alijis: 1.Repair and Rehabilitation of Typhoon Tino–Affected Campus Buildings – 350k 2. Repair of Chemistry and Physics Laboratory– 100k 3. Conversion, Enhancement and Rehabilitation of of Existing Laboratory Facilities and Open Areas into Academic Classrooms– 480K
4.Upgrading and Repair of Campus Restrooms in Compliance with GAD Standards (Automotive and Mechanical Building) – 620K 5.Rehabilitation of the Covered Court Rainwater and Storm Drainage System – 860K 6.Repair of STGB Ground Floor Restrooms and Conversion to All-Gender Facilities – 350K
7.Rehabilitation of Second Floor Comfort Rooms, Academic Building 1 – 200K 8.Rehabilitation of Computer Laboratory 6 – 260K 9.Repair and Rehabilitation of Gate 2 and Guard House – 180K
Fortune Towne 1.Upgrading of Electrical System: Replacement of Transformer and rehabilitation of electrical lines (Phase 1) – 500K 2.Upgrading of the Drainage System (Phase 2) – 800K 3.Retrofitting of Connecting Bridge Between IT Building and CBMA Building – 705K
4.Expansion and Enhancement of Parking Spaces with Garage Relocation – 500K 5.Enhancement of Student Park – 250K 6.Installation of Fascia at IT Building Roof Deck Roofing Right Wing (Phase 1) – 100K 7.Concreting of Open Court – 445K
BINALBAGAN: 1. Repair and Enhancement of New Admin Building (Accounting and Budget Office) Phase 2 at CHMSU-Binalbagan Campus-650K 2. Repair and Enhancement of New Admin Building (Registrar Office) at CHMSU-Binalbagan Campus-600K 3. Repair and Enhancement of Student Center (OSAS Office) Phase 2 at CHMSU-Binalbagan Campus-350K
4. Repair of DRRM Office and Dojo Room at CHMSU-Binalbagan Campus)-200K 5. Enhancement of H.E Room at CHMSU-Binalbagan Campus-170K 6. Enhancement of Guidance Office-1.215M
7. Enhancement of Clinic at CHMSU-Binalbagan Campus-150K 9. Rehabilitation of Sewage System at CHMSU-Binalbagan Campus-65K 10. Labor and Materials for Electrical Installation for Rooms 3 & 4 - IT Laboratory-70K
Talisay 1. Re-engineering of Access Road and Drainage Rehabilitation with Parking Slots at the Back of LSA Building, Phase 3, Talisay Main Campus – 1.8M 2. Replacement of Lighting Fixtures at Laboratory Rooms (103-107) – 100K 3. Rehabilitation of LSAB Female Toilet (2F & 3F) Left Wing – 1.6M
4.Supply of Solar Light at the back of LSA Building – 283K 5.Rehabilitation of Girls Dormitory Phase 2 – 500K 6.FDAS Rehabilitation at ETGB – 300K
7. Enhancement of Board Room Toilet – 60K 8. Enhancement of Drainage between College of Engineering Building and University Gymnasium – 150K 9. Repair of Roofing Leaks and Insulation Replacement at University Gymnasium – 350K
10. Rehabilitation of Roofing, Concrete Gutter, and Storm Drainage System with Ceiling Replacement at LSAB – 760K 11. Rehabilitation of Drainage System and Drainage Cover Beside Football Field -CHMSU Main Campus – 250K
C. MONITORING
ITEM |  | DETAILS
Monitoring Frequency |  | Quarterly
Reporting Office
| Prepared by: |  |  | Reviewed by: |  |  |  | Approved by:
| Division/Unit Head/Dean |  |  | Vice President |  |  |  | SUC III President