## Sheet1
RESULTS-BASED ACTION PLAN
For FY 2026
A. BASIC INFORMATION
ITEM |  | DETAILS
Campus |  | Campus-wide
Office/Unit |  | Quality Management
Program/Project/Activity/KRA |  | ISO, AACCUP, COPC, AUN-QA etc.
Strategic Alignment/Planning Document |  | CHMSU Strategic Plan 2025-2029/Administrative Manual/Applicable CMOs/GAM/Procurement Law, etc
Breakthrough Goals |  | 1. Cutting-Edge Knowledge and 21st Century Skills (Education for Sustainable Education) 5. Internationalization
Strategic Objectives/Mandate |  | SO1. To offer innovative Industry 4.0-driven, and ESD-oriented academic programs and learning opportunities that meet the demands of the local, regional, and global community and CHED priorities. SO8. To Broaden the University's collaboration and partnerships with relevant local, national, and international institutions in support of and to complement its instruction, research, engagement, and good governance functions."
Planning Year |  | 2026
Date Prepared |  | January 13, 2026
B. RESULTS-BASED ACTION PLAN MATRIX
Result Level | Target Result (SMART) | Key Actions/Activities | Key Risk | Mitigation/Control Measures | Key Performance Output/Outcome Indicators | Target | Responsible Office/Person | Timeline | Fund Source | Budget Requirements | Budget Allocation (Based on 2026 Budget) | Budget Deficit | Means of Verification (MOV)
COPC – Certificate of Program Compliance
OUTCOME 1 | By 2026, the University achieves Certificate of Program Compliance (COPC) for selected new and existing programs, ensuring compliance with CHED standards. | • Facilitate CHED evaluation and site visit | Non-compliance with CHED requirements, delayed submission of documents | • Early preparation of documents | Number of programs granted COPC | 1 program with COPC | OVPAA, QM, Deans, Program Chairs | 2026 | GAA / College Fund
|  | • Prepare required documentation and evidence |  | • Internal mock visits•
|  | • Implement recommendations from CHED pre-assessment |  | Designate responsible focal persons for each program
OUTPUT 1.1 | By 2026, selected academic programs complete all requirements and are ready for COPC assessment. | • Compile program documents and curriculum maps | Incomplete documentation, late submission | • Internal review and mentoring | Programs ready for COPC assessment | 4 programs with COPC | OVPAA, QM, Deans, Program Chairs, | 2026 | GAA / Internal Fund
|  | • Conduct internal audit/mock visit |  | • Follow-up with CHED for schedule confirmation
• Submit documents to CHED for evaluation
ISO – International Organization for Standardization
OUTCOME 1 | By 2026, the University maintains ISO 9001:2015 certification by conducting internal audits and successfully passing surveillance audits. | • Plan and conduct internal audits | Non-compliance with ISO standards, delays in audit preparation | • Audit schedule planning | Number of audits conducted and ISO surveillance audits passed | 2 internal audits, 2 surveillance audits successfully passed | OVPAA, QM Office, Internal Audit Team | 2026 | GAA / QM Fund
|  | • Prepare documentation for surveillance audits |  | • Internal audit team training
|  | • Implement corrective actions from audits |  | • Immediate corrective action for non-conformities
OUTPUT 1.1 | Conduct 2 Internal Audits | • Plan and conduct 2 internal audits of ISO 9001:2015 processes | Incomplete audit coverage, delayed corrective actions | • Prepare audit plan and checklist | Internal audit reports completed and corrective actions implemented | 2 internal audits conducted | QM Office, Internal Audit Team | 2026 | GAA / QM Fund
|  | • Document findings and corrective actions |  | • Assign trained internal auditors
• Follow-up on non-conformities
OUTPUT 1.2 | Conduct 2 ISO Surveillance Audits | • Prepare documentation and evidence for ISO surveillance audits | Non-compliance with ISO standards, incomplete documentation | • Conduct pre-audit review | 2 surveillance audits successfully passed | 2 surveillance audits passed | QM Office, OVPAA, Internal Audit Team | 2026 | GAA / QM Fund
|  | • Host 2 surveillance audits by the certifying body |  | • Immediate corrective/preventive action
• Implement audit recommendations
AACCUP – Accrediting Agency of Chartered Colleges and Universities in the Philippines
OUTCOME 1 | By 2026, the University successfully completes AACCUP program accreditation surveys for all applicable levels (PSV, Level I, III, IV), ensuring compliance with CHED and accreditation standards. | • Facilitate survey visits for Level IV, and Level II | Incomplete documentation, low faculty participation, non-compliance with AACCUP standards | • Early document preparation | Number of programs successfully surveyed and accredited by AACCUP | Level IV – 5 survey visits Level III – 1 survey visit Level I – 5 survey visits PSV – 5 facilitation visits | OVPAA, QM Office, Deans, Program Chairs | 2026 | GAA / QM Fund
|  | • Prepare and submit Compliance Matrix and supporting documents |  | • Mock assessments and mentoring
|  | • Implement recommendations from mock/internal audits |  | • Assign focal persons per program
OUTPUT 1.1 | Conduct Level IV Survey Visits | • Facilitate 5 Level IV survey visits | Incomplete evidences, low faculty engagement | • Internal review and mentoring | Number of Level IV survey visits successfully facilitated | 5 Level IV survey visits | QM Office, OVPAA, Deans, Program Chairs | 2026 | GAA / QM Fund
|  | • Prepare programs’ documents and Compliance Matrix |  | • Assign focal persons
• Implement recommendations from mock/internal audits
OUTPUT 1.2 | Conduct Level III Survey Visit | • Facilitate 1 Level III survey visit | Incomplete documentation, non-compliance with standards | • Internal review and mentoring | Number of Level III survey visits successfully facilitated | 1 Level II survey visit | QM Office, OVPAA, Deans, Program Chairs | 2026 | GAA / QM Fund
|  | • Prepare and submit the Compliance Matrix |  | • Assign responsible program focal persons
• Address recommendations from pre-assessment audits
OUTPUT 1.3 | Conduct Level I Survey Visits | • Facilitate 5 Level I survey visits • Prepare Compliance Matrix and other documentation • Conduct internal reviews | Delays in documentation, faculty unpreparedness | • Mock internal audits • Mentoring and training sessions | Number of Level I survey visits successfully facilitated | 5 Level I survey visits | QM Office, OVPAA, Deans, Program Chairs | 2026 | GAA / QM Fund
OUTPUT 1.4 | Facilitation of PSV (Pre-Survey Visit) | • Facilitate 5 PSV visits for programs • Prepare documents and Compliance Matrix • Conduct pre-survey audits and mentoring | Incomplete preparation, delays in scheduling | • Early scheduling and assignment of focal persons • Mock audits | Number of PSV facilitation visits successfully conducted | 5 PSV visits | QM Office, OVPAA, Deans, Program Chairs | 2026 | GAA / QM Fund
AUN-QA – ASEAN University Network – Quality Assurance
OUTCOME 1 | By 2026, the University increases its active membership in national and international professional organizations and networks to strengthen academic collaboration and global engagement. | • Identify relevant professional organizations | Limited funding and low participation | • Allocate annual membership budget | No. of memberships in national/international professional organizations | At least 1 active membership | OVPAA, | 2026 | GAA / QM & AUN-QA Fund
|  | • Apply for institutional memberships |  | • Designate focal persons per organization |  |  | QM Office
• Sustain active participation in networks and activities
OUTPUT 1.1 | By 2027, the University secures new institutional memberships in priority national and international professional organizations. | • Identify priority organizations• Prepare and submit membership applications• Payment of membership dues | Delays in approval or incomplete requirements | • Early document preparation | No. of memberships approved | 1 new membership | OVPAA | 2026-04-01 | GAA / QM & AUN-QA Fund
|  |  |  | • Assigned focal persons |  |  | QM Office
OUTPUT 1.2 | By 2026, the University sustains active participation in national and international professional networks. | • Participate in meetings and activities | Low participation rate | • Monitoring of participation | No. of active memberships maintained | 1 active membership | OVPAA | 2026 | GAA / QM & AUN-QA Fund
|  | • Submit required reports and renewals |  | • Annual performance review |  |  | QM Office
OUTCOME 2 | By 2026, the University will achieve AUN-QA Program Assessment for selected academic programs, ensuring compliance with ASEAN and international quality standards. | • Conduct AUN-QA readiness assessment | Programs not fully compliant with AUN-QA standards | • Mock assessments and internal QA audits | No. of programs with AUN-QA Programme Assessment | 4 AUN-QA Programme Assessment | OVPAA | 2026-2027 | GAA / QM & AUN-QA Fund
|  | • Prepare and review Self-Assessment Reports (SAR) |  | • Capacity-building for faculty and QA teams |  |  | QM Office
|  | • Implement continuous quality improvements |  |  |  |  | Deans
Program Chairs
OUTPUT 2.1 | By 2026, selected academic programs complete AUN-QA readiness assessment and Self-Assessment Report (SAR) preparation. | • Conduct AUN-QA orientation and training• Prepare SARs• Conduct mock assessments | Incomplete SAR documentation | • QA mentoring and internal reviews | No. of programs ready for AUN-QA assessment | 4 programs | OVPAA | 2026 | GAA / QM Fund
QM Office
Deans
Program Chairs
OUTPUT 2.2 | By 2027, at least four academic program will have been granted an AUN-QA Programme Assessment. | • Submit SAR to AUN-QA• Host AUN-QA assessment visit• Address recommendations | Non-compliance with AUN-QA criteria | • Pre-assessment audits• Continuous improvement actions | No. of programs granted AUN-QA Programme Assessment | 4 Programme Assessment | OVPAA QM Office Deans Program Chairs | 2026–2027 | GAA / AUN-QA Fund
PQA – Philippine Quality Award
OUTCOME 1 | By 2026, the University successfully applies for and advances in the Philippine Quality Award (PQA), demonstrating organizational excellence and compliance with PQA criteria. | • Prepare PQA application and required documentation • Conduct internal self-assessment and gap analysis • Host PQA evaluation visit and implement recommendations | Incomplete or delayed application, non-compliance with PQA criteria | • Assign dedicated PQA focal persons • Conduct internal review and mock assessment • Early submission and follow-up with PQA Secretariat | Status of PQA application and progress in award evaluation | Submit PQA application and achieve the next award level | QM Office, OP, OVPAA, OVPAF, VVPREIP | 2026 | GAA / QM Fund
OUTPUT 1.1 | Prepare and Submit PQA Application | • Compile required documentation for PQA application • Conduct internal self-assessment and gap analysis • Prepare organizational performance reports | Missing or incomplete documentation, delayed submission | • Assign dedicated focal persons per criteria • Internal review and mentoring of responsible units | PQA application submitted on time and complete | 1 PQA application submitted | QM Office, OP, OVPAA, OVPAF, VVPREIP | 2026 | GAA / QM Fund
OUTPUT 1.2 | Facilitate PQA Evaluation Visit | • Host PQA evaluation visit • Provide evidence and documentation to PQA assessors• Implement corrective actions or recommendations from evaluators | Non-compliance with PQA criteria, incomplete documentation | • Pre-visit mock evaluation • Assign focal persons for each criteria area • Follow-up on pre-assessment findings | PQA evaluation visit conducted and recommendations addressed | 1 PQA evaluation visit successfully facilitated | QM Office, OP, OVPAA, OVPAF, VVPREIP | 2026 | GAA / QM Fund
C. Monitoring
ITEM |  | DETAILS
Monitoring Frequency |  | Quarterly
Means of Verification |  | COPC – Certificate of Program Compliance Outcome 1: Official CHED COPC certificate CHED site visit report and recommendations Output 1.1: Submission receipt of required documents Internal audit/mock visit reports
ISO – International Organization for Standardization Output 1.1: Internal audit reports Corrective action reports Audit checklists and schedules Output 1.2: ISO surveillance audit reports Certificates of audit completion Corrective action reports and evidence of implementation
AACCUP – Accrediting Agency of Chartered Colleges and Universities in the Philippines Output 1.1: AACCUP Level IV survey report Submitted Compliance Reports and supporting documents Mock assessment reports and QM review notes Meeting minutes of Deans, Program Chairs, Faculty and QM team Output 1.2: AACCUP Level III survey report Submitted Compliance Report and supporting documents Mock assessment Output 1.3: Official AACCUP Level I survey reports Compliance Report submitted to AACCUP Internal mock assessment reports Evidence of faculty preparation/training Output 1.4: AACCUP PSV reports Submitted Compliance Report and supporting documents Mock/internal audit reports Meeting minutes of QM team and program faculty
AUN-QA – ASEAN University Network – Quality Assurance Outcome 1: Official membership certificates from organizations Output 1.1: Approved membership certificates or letters from organizations Copies of submitted membership applications Payment receipts for membership dues Output 1.2: Attendance records of meetings, conferences, or webinars Reports or minutes documenting participation and contributions Renewal confirmations of memberships Annual performance/activity reports Outcome 2: Official AUN-QA Programme Assessment certificates or approval letters Final assessment reports from AUN-QA Output 2.1: Completed Self-Assessment Reports (SARs) Attendance sheets of orientation and training sessions Output 2.2: Official AUN-QA assessment certificates Final AUN-QA assessment report Documentation showing implementation of recommendations or improvements Meeting minutes or reports during the assessment visit
PQA – Philippine Quality Award Output 1.1: Official PQA application receipt Self-assessment report and gap analysis documents Organizational performance reports Minutes of meetings reviewing application readiness Output 1.2: PQA evaluation report and assessor feedback Corrective action reports addressing assessor recommendations Evidence submitted during evaluation visit (documents, data, presentations) Minutes of post-visit review meetings
Reporting Office |  | Quality Management Office
| Prepared by: |  |  | Reviewed and approved by:
| YRIKA MARIE R. DUARAN, PhDTM |  |  | NORBERTO P. MANGULABNAN, PhD
| Division/Unit Head/Dean |  |  | SUC III President